## current file
Job | Country | Customer | Type | Job Status | Onshore/ Offshore | String | Expected date | Finish date | duration | # of FSS | FSS1 assigned | FSS2 assigned | Conflicts
7 | Egypt | BP | Vacation | Ongoing | Offshore | 9 5/8- 80.8 PPF- C110- TSH Blue Riser | 2019-02-15 | 2019-02-21 | 6 | 1 | Carlos Lopez | na
13 | Pakistan | ENI | Standby | Ongoing | Offshore |  | 2019-02-17 | 2019-02-27 | 10 | 2 | Hussein | Bashar
7 | Egypt | Burullus | Active | Planned | Onshore- Inspection |  | 2019-02-20 | 2019-02-23 | 3 | 1 | Amir Salem | na
8 | Egypt | Vacation | Active | Planned | Offshore |  | 2019-02-21 | 2019-02-28 | 7 | 1 | Carlos Lopez | na
11 | Egypt | Petrobel- ZOHR | Active | Planned | Offshore |  | 2019-02-23 | 2019-03-02 | 7 | 1 | Amir Salem | na
3 | Kurdistan | DNO | Active | Planned | Onshore | 16"- 96 PPF- L80- TSH W513 | 2019-02-24 | 2019-03-26 | 30 | 1 | Wiliam Burnett | na
2 | Egypt, Cairo | Burullus | Vacation | Planned | Offshore | 14- 113 PPF- P110- TSH W623 DPLS in stands | 2019-02-28 | 2019-03-10 | 10 | 2 | Hussein | Shalaby
10 | Egypt | Petrobel | Active | Planned | Aburudis |  | 2019-02-28 | 2019-03-14 | 14 | 1 | AbuSaif | na
5 | Libya | Mellitah | Active | Planned | Offshore | 4 1/2- 11.6 PPF- Sanicro 28- 110 KSI- TSh Blue DPLS | 2019-03-02 | 2019-03-17 | 15 | 1 | Akram Haroon | na
17 | Tunisia | OMV | Active | Planned | Inspection |  | 2019-03-15 | 2019-03-30 | 15 | 1 | To be confirmed | na
15 | Libya | ENI NA | Vacation | Planned | Onshore- Inspection |  | 2019-03-17 | 2019-03-24 | 7 | 1 | Akram Haroon | na | Fix the visa for shalaby
14 | Pakistan | ENI | Active | Planned | Offshore |  | 2019-03-20 | 2019-03-30 | 10 | 2 | Hussein | Shalaby | Fix the visa for shalaby
9 | Egypt | Petrobel | Vacation | Planned | Onshore W563 |  | 2019-04-01 | 2019-04-13 | 12 | 1 | AbuSaif | na
4 | Egypt | Vacation | Active | Planned | Unsnuffing | 3 1/2 and 2 7/8 | 2019-05-01 | 2019-05-06 | 5 | 1 | AbuSaif | na
12 | Pakistan | MOL | Standby | Planned | Stock count |  | 2019-05-01 | 2019-05-11 | 10 | 1 | Hussein | na
16 | Tunisia | ENI | Active | Planned | Running Assistance |  | 2019-07-01 | 2019-07-11 | 10 | 1 | Hussein | na
Formulas:
Finish date = [Expected date]+6

## Sheet1
Customer | Expected_date | Finish date | FSS1 assigned | FSS2 assigned | Conflicts
BP | 2019-02-15 | 2019-02-21 | Carlos Lopez
ENI | 2019-02-17 | 2019-02-27 | Hussein | Bashar
Burullus | 2019-02-20 | 2019-02-23 | Salem, Amir
BP | 2019-02-22 | 2019-03-01 | Carlos Lopez
Petrobel- ZOHR | 2019-02-23 | 2019-03-02 | Amir Salem |  |  | FALSE
DNO | 2019-02-24 | 2019-03-26 | Wiliam Burnett
Burullus | 2019-02-28 | 2019-03-10 | Hussein | Shalaby
Petrobel | 2019-02-28 | 2019-03-14 | Abusaif
Mellitah | 2019-03-02 | 2019-03-17 | Akram Haroon
OMV | 2019-03-15 | 2019-03-30 | To be confirmed
ENI NA | 2019-03-17 | 2019-03-24 | Akram Haroon |  | Fix the visa for shalaby
ENI | 2019-03-20 | 2019-03-30 | Hussein | Shalaby | Fix the visa for shalaby
Petrobel | 2019-04-01 | 2019-04-13 | AbuSaif
AGIBA | 2019-05-01 | 2019-05-06 | AbuSaif
MOL | 2019-05-01 | 2019-05-11 | Hussein
ENI | 2019-07-01 | 2019-07-11 | Hussein
Formulas:
Finish date = [Expected_date]+6

## Sheet1 (2)
Customer | Expected_date | Finish date | FSS1 assigned | FSS2 assigned | Conflicts
BP | 2019-02-15 | 2019-02-21 | Carlos Lopez
ENI | 2019-02-17 | 2019-02-27 | Hussein | Bashar
Burullus | 2019-02-20 | 2019-02-23 | Salem, Amir
BP | 2019-02-19 | 2019-02-26 | Carlos Lopez
Petrobel- ZOHR | 2019-02-23 | 2019-03-02 | Amir Salem |  |  | TRUE
DNO | 2019-02-24 | 2019-03-26 | Wiliam Burnett
Burullus | 2019-02-28 | 2019-03-10 | Hussein | Shalaby
Petrobel | 2019-02-28 | 2019-03-14 | Abusaif
Mellitah | 2019-03-02 | 2019-03-17 | Akram Haroon
OMV | 2019-03-15 | 2019-03-30 | To be confirmed
ENI NA | 2019-03-17 | 2019-03-24 | Akram Haroon |  | Fix the visa for shalaby
ENI | 2019-03-20 | 2019-03-30 | Hussein | Shalaby | Fix the visa for shalaby
Petrobel | 2019-04-01 | 2019-04-13 | AbuSaif
AGIBA | 2019-05-01 | 2019-05-06 | AbuSaif
MOL | 2019-05-01 | 2019-05-11 | Hussein
ENI | 2019-07-01 | 2019-07-11 | Hussein
Formulas:
Finish date = [Expected_date]+6

## Poposed file
Date | Amir | Abusaif | Hussein | Bashar | Carlos Lopez | William Burnett | Shalaby | Akram Haroon
2019-02-17 |  |  | Eni Pakistan | ENI Pakistan | BP |  |  |  | Job | Country | Customer | Job Status | Onshore/ Offshore | String | Expected date | Finish date | duration | # of FSS | FSS1 assigned | FSS2 assigned
2019-02-18 | [8 empty] | 7 | Egypt | BP | Ongoing | Offshore | 9 5/8- 80.8 PPF- C110- TSH Blue Riser | 2019-02-15 | 2019-02-21 | 6 | 1 | Carlos Lopez | N/A
2019-02-19 | [8 empty] | 13 | Pakistan | ENI | Ongoing | Offshore |  | 2019-02-17 | 2019-02-27 | 10 | 2 | Hussein | Bashar
2019-02-20 | Burrullus inspection | [7 empty] | 7 | Egypt | Burullus | Planned | Onshore- Inspection |  | 2019-02-20 | 2019-02-23 | 3 | 1 | Salem, Amir | N/A
2019-02-21 |  |  |  |  | BP |  |  |  | 8 | Egypt | BP | Planned | Offshore |  | 2019-02-21 | 2019-02-28 | 7 | 1 | Carlos Lopez | N/A
2019-02-22 | [8 empty] | 11 | Egypt | Petrobel- ZOHR | Planned | Offshore |  | 2019-02-23 | 2019-03-02 | 7 | 1 | Salem, Amir | N/A
2019-02-23 | Petrobel Zohr | [7 empty] | 3 | Kurdistan | DNO | Planned | Onshore | 16"- 96 PPF- L80- TSH W513 | 2019-02-24 | 2019-03-26 | 30 | 1 | Wiliam Burnett | N/A
2019-02-24 | [5 empty] | DNO |  |  | 2 | Egypt | Burullus | Planned | Offshore | 14- 113 PPF- P110- TSH W623 DPLS in stands | 2019-02-28 | 2019-03-10 | 10 | 2 | Hussein | Shalaby
2019-02-25 | [8 empty] | 10 | Egypt | Petrobel | Planned | Aburudis |  | 2019-02-28 | 2019-03-14 | 14 | 1 | Abusaif | N/A
2019-02-26 | [8 empty] | 5 | Libya | Mellitah | Planned | Offshore | 4 1/2- 11.6 PPF- Sanicro 28- 110 KSI- TSh Blue DPLS | 2019-03-02 | 2019-03-17 | 15 | 1 | Akram Haroon | N/A
2019-02-27 | [8 empty] | 15 | Libya | ENI NA | Planned | Onshore- Inspection |  | 2019-03-17 | 2019-03-24 | 7 | 1 | Akram Haroon | N/A
2019-02-28 |  | Petrobel 3 CR | Burrullus running |  |  |  | Burrullus running |  | 17 | Tunisia | OMV | Planned | Inspection |  | 2019-03-15 | 2019-03-30 | 15 | 1 | To be confirmed | N/A | Fix the visa for shalaby
2019-03-01 | [8 empty] | 14 | Pakistan | ENI | Planned | Offshore |  | 2019-03-20 | 2019-03-30 | 10 | 2 | Hussein | Shalaby | Fix the visa for shalaby
2019-03-02 | [7 empty] | Mellitah | 9 | Egypt | Petrobel | Planned | Onshore W563 |  | 2019-04-01 | 2019-04-13 | 12 | 1 | AbuSaif | N/A
2019-03-03 | [8 empty] | 4 | Egypt | AGIBA | Planned | Unsnuffing | 3 1/2 and 2 7/8 | 2019-05-01 | 2019-05-06 | 5 | 1 | AbuSaif | N/A
2019-03-04 | [8 empty] | 12 | Pakistan | MOL | Planned | Stock count |  | 2019-05-01 | 2019-05-11 | 10 | 1 | Hussein | N/A
2019-03-05 | [8 empty] | 16 | Tunisia | ENI | Planned | Running Assistance |  | 2019-07-01 | 2019-07-11 | 10 | 1 | Hussein | N/A
2019-03-06
2019-03-07
2019-03-08
2019-03-09
2019-03-10
2019-03-11
2019-03-12
2019-03-13
2019-03-14
2019-03-15
2019-03-16
2019-03-17
2019-03-24 |  |  | Eni Pakistan |  |  |  | Eni Pakistan | ENI NA
2019-03-31 |  | Petrobel
2019-04-07
2019-04-14
2019-04-21
2019-04-28 |  | Agiba | MOL
2019-05-05
2019-05-12
2019-05-19
2019-05-26
2019-06-02
2019-06-09
2019-06-16
2019-06-23
2019-06-30 |  |  | ENI Tunisia