## Main File
Job | Expected date | Finish date | FSS1 assigned | FSS2 assigned | # of FSS | Customer | Type | Job Status | Onshore/ Offshore | duration | Country | OD | RIG | Sub BU | BU | Well | Rate
7 | 2019-02-15 | 2019-02-21 | Carlos Lopez | Bashar | 1 | BP | Vacation | Ongoing | Offshore | 6 | Egypt | 4.5 " | AD-68 | OMENA | DIMI | h1
13 | 2019-01-17 | 2019-01-27 | Hussein | Bashar | 2 | ENI | Standby | Ongoing | Offshore | 10 | Pakistan | 4.5 " | AD-68 | NS | DINS | h2
7 | 2019-01-20 | 2019-01-23 | Salem, Amir | na | 1 | Burullus | Active | Planned | Onshore- Inspection | 3 | Egypt | 4.5 " | Al Hail | OMENA | DIMI | h3
8 | 2019-02-21 | 2019-02-28 | Carlos Lopez | na | 1 | Vacation | Active | Planned | Offshore | 7 | Egypt | 4.5 " | SMS FAITH | OMENA | DIMI | h4
11 | 2019-02-23 | 2019-03-02 | Amir Salem | na | 1 | Petrobel- ZOHR | Active | Planned | Offshore | 7 | Egypt | 4.5 " | SMS FAITH | OMENA | DIMI | h5
3 | 2019-02-24 | 2019-03-26 | Wiliam Burnett | na | 1 | DNO | Active | Planned | Onshore | 30 | Kurdistan | 6 5/8" | AD-67 | NS | DINS | h6
2 | 2019-02-28 | 2019-03-10 | Hussein | Shalaby | 2 | Burullus | Vacation | Planned | Offshore | 10 | Egypt, Cairo | 9 5/8" | AD-66 | OMENA | DIMI | h7
10 | 2019-02-28 | 2019-03-14 | TBC1 | na | 1 | Petrobel | Active | Planned | Aburudis | 14 | Egypt | 9 5/8" | AD-66 | OMENA | DIMI | h8
5 | 2019-03-02 | 2019-03-17 | Akram Haroon | na | 1 | Mellitah | Active | Planned | Offshore | 15 | Libya | 9 5/8" | AD-131 | SSA | DINS | h9
17 | 2019-03-15 | 2019-03-30 | TBC1 | na | 1 | OMV | Active | Planned | Inspection | 15 | Tunisia | 9 5/8" | AD-131 | SSA | DINS | h10
15 | 2019-03-17 | 2019-03-24 | Akram Haroon | na | 1 | ENI NA | Vacation | Planned | Onshore- Inspection | 7 | Libya | 6 5/8" | AD-66 | SSA | DINS | h11
14 | 2019-03-20 | 2019-03-30 | Hussein | Shalaby | 2 | ENI | Active | Planned | Offshore | 10 | Pakistan | 6 5/8" | AD-66 | NS | DINS | h12
9 | 2019-04-01 | 2019-04-13 | TBC1 | na | 1 | Petrobel | Vacation | Planned | Onshore W563 | 12 | Egypt | 6 5/8" | AD-68 | OMENA | DIMI | h13
4 | 2019-05-01 | 2019-05-06 | AbuSaif | na | 1 | Vacation | Active | Planned | Unsnuffing | 5 | Egypt | 6 5/8" | AD-68 | OMENA | DIMI | h14
12 | 2019-08-01 | 2019-08-11 | Hussein | na | 1 | MOL | Standby | Planned | Stock count | 10 | Pakistan | 6 5/8" | AD-130 | SSA | DINS | h15
16 | 2019-06-11 | 2019-06-21 | Hussein | na | 1 | ENI | Active | Planned | Running Assistance | 10 | Tunisia | 6 5/8" | AD-130 | SSA | DINS | h16
17 | 2019-07-01 | 2019-07-08 | Carlos Lopez | na | 1 | Vacation | Active | Planned | Offshore | 7 | Egypt | 6 5/8" | AD-131 | OMENA | DIMI | h17
18 | 2019-10-24 | 2019-10-28 | Sahoo, Bibekananda | na | 1 | ADNOC | Active | Planned | Offshore | 4 | UAE | 4.5 " | AD-68 | GCC | DIMI | h18
18 | 2019-10-24 | 2019-10-28 | Milton Machado | na | 1 | ADNOC | Active | Planned | Offshore | 4 | UAE | 4.5 " | AD-68 | GCC | DIMI | h19
19 | 2019-10-30 | 2019-11-01 | Sahoo, Bibekananda | na | 1 | ADNOC | Active | Planned | Offshore | 2 | UAE | 4.5 " | Al Hail | GCC | DIMI | h20
20 | 2019-10-30 | 2019-11-04 | Al Yaarabi, Yahya | na | 1 | ADNOC | Active | Planned | Offshore | 5 | UAE | 4.5 " | SMS FAITH | GCC | DIMI | h21
20 | 2019-10-30 | 2019-11-04 | Bhogavilli, Bala Ranjith Kumar | na | 1 | ADNOC | Active | Planned | Offshore | 5 | UAE | 4.5 " | SMS FAITH | GCC | DIMI | h22
21 | 2019-10-30 | 2019-11-04 | TBC1 | na | 1 | ADNOC | Active | Planned | Offshore | 5 | UAE | 6 5/8" | AD-67 | GCC | DIMI | h23
22 | 2019-11-01 | 2019-11-07 | TBC1 | na | 1 | ADNOC | Active | Planned | Offshore | 6 | UAE | 9 5/8" | AD-66 | GCC | DIMI | h24
23 | 2019-11-03 | 2019-11-07 | TBC2 | na | 1 | ADNOC | Active | Planned | Offshore | 4 | UAE | 9 5/8" | AD-66 | GCC | DIMI | h25
24 | 2019-11-05 | 2019-11-11 | TBC1 | na | 1 | ADNOC | Active | Planned | Offshore | 6 | UAE | 9 5/8" | AD-131 | GCC | DIMI | h26
25 | 2019-11-07 | 2019-11-11 | TBC2 | na | 1 | ADNOC | Active | Planned | Offshore | 4 | UAE | 9 5/8" | AD-131 | GCC | DIMI | h27
26 | 2019-11-15 | 2019-11-21 | TBC1 | na | 1 | ADNOC | Active | Planned | Offshore | 6 | UAE | 6 5/8" | AD-66 | GCC | DIMI | h28
27 | 2019-11-17 | 2019-11-21 | TBC2 | na | 1 | ADNOC | Active | Planned | Offshore | 4 | UAE | 6 5/8" | AD-66 | GCC | DIMI | h29
28 | 2019-11-18 | 2019-11-24 | TBC1 | na | 1 | ADNOC | Active | Planned | Offshore | 6 | UAE | 9 5/8" | AD-68 | GCC | DIMI | h30
29 | 2019-11-20 | 2019-11-24 | TBC2 | na | 1 | ADNOC | Active | Planned | Offshore | 4 | UAE | 9 5/8" | AD-68 | GCC | DIMI | h31
30 | 2019-11-20 | 2019-11-26 | TBC1 | na | 1 | ADNOC | Active | Planned | Offshore | 6 | UAE | 9 5/8" | AD-130 | GCC | DIMI | h32
31 | 2019-11-22 | 2019-11-26 | TBC2 | na | 1 | ADNOC | Active | Planned | Offshore | 4 | UAE | 9 5/8" | AD-130 | GCC | DIMI | h33
32 | 2019-11-20 | 2019-11-26 | TBC1 | na | 1 | ADNOC | Active | Planned | Offshore | 6 | UAE | 9 5/8" | AD-131 | GCC | DIMI | h34
33 | 2019-11-22 | 2019-11-26 | TBC2 | na | 1 | ADNOC | Active | Planned | Offshore | 4 | UAE | 6 5/8" | AD-131 | GCC | DIMI | h35
34 | 2019-11-25 | 2019-11-30 | TBC1 | na | 1 | ADNOC | Active | Planned | Offshore | 5 | UAE | 9 5/8" | AD-69 | GCC | DIMI | h36
35 | 2019-11-27 | 2019-11-30 | TBC2 | na | 1 | ADNOC | Active | Planned | Offshore | 3 | UAE | 9 5/8" | AD-69 | GCC | DIMI | h37
Formulas:
Finish date = [Expected date]+6

## current file
Job | Country | Customer | Type | Job Status | Onshore/ Offshore | Expected date | Finish date | duration | # of FSS | FSS1 assigned | FSS2 assigned | Conflicts | String
7 | Egypt | BP | Vacation | Ongoing | Offshore | 2019-02-15 | 2019-02-21 | 6 | 1 | Carlos Lopez | na |  | 9 5/8- 80.8 PPF- C110- TSH Blue Riser
13 | Pakistan | ENI | Standby | Ongoing | Offshore | 2019-02-17 | 2019-02-27 | 10 | 2 | Hussein | Bashar
7 | Egypt | Burullus | Active | Planned | Onshore- Inspection | 2019-02-21 | 2019-02-24 | 3 | 1 | Amir Salem | na
8 | Egypt | Vacation | Active | Planned | Offshore | 2019-02-21 | 2019-02-28 | 7 | 1 | Carlos Lopez | na
11 | Egypt | Petrobel- ZOHR | Active | Planned | Offshore | 2019-02-23 | 2019-03-02 | 7 | 1 | Amir Salem | na
3 | Kurdistan | DNO | Active | Planned | Onshore | 2019-02-24 | 2019-03-26 | 30 | 1 | Wiliam Burnett | na |  | 16"- 96 PPF- L80- TSH W513
2 | Egypt, Cairo | Burullus | Vacation | Planned | Offshore | 2019-02-28 | 2019-03-10 | 10 | 2 | Hussein | Shalaby |  | 14- 113 PPF- P110- TSH W623 DPLS in stands
10 | Egypt | Petrobel | Active | Planned | Aburudis | 2019-02-28 | 2019-03-14 | 14 | 1 | AbuSaif | na
5 | Libya | Mellitah | Active | Planned | Offshore | 2019-03-02 | 2019-03-17 | 15 | 1 | Akram Haroon | na |  | 4 1/2- 11.6 PPF- Sanicro 28- 110 KSI- TSh Blue DPLS
17 | Tunisia | OMV | Active | Planned | Inspection | 2019-03-15 | 2019-03-30 | 15 | 1 | To be confirmed | na
15 | Libya | ENI NA | Vacation | Planned | Onshore- Inspection | 2019-03-17 | 2019-03-24 | 7 | 1 | Akram Haroon | na | Fix the visa for shalaby
14 | Pakistan | ENI | Active | Planned | Offshore | 2019-03-20 | 2019-03-30 | 10 | 2 | Hussein | Shalaby | Fix the visa for shalaby
9 | Egypt | Petrobel | Vacation | Planned | Onshore W563 | 2019-04-01 | 2019-04-13 | 12 | 1 | AbuSaif | na
4 | Egypt | Vacation | Active | Planned | Unsnuffing | 2019-05-01 | 2019-05-06 | 5 | 1 | AbuSaif | na |  | 3 1/2 and 2 7/8
12 | Pakistan | MOL | Standby | Planned | Stock count | 2019-05-01 | 2019-05-11 | 10 | 1 | Hussein | na
16 | Tunisia | ENI | Active | Planned | Running Assistance | 2019-07-01 | 2019-07-11 | 10 | 1 | Hussein | na
Formulas:
Finish date = [Expected date]+6

## Sheet1
Job | Expected_date | Finish date | FSS1 assigned | FSS2 assigned | # of FSS | Customer | Type | Job Status | Onshore/ Offshore | duration | Country
7 | 2019-02-15 | 2019-02-21 | Carlos Lopez |  | 1 | BP | Vacation | Ongoing | Offshore | 6 | Egypt
13 | 2019-02-17 | 2019-02-27 | Hussein | Bashar | 2 | ENI | Standby | Ongoing | Offshore | 10 | Pakistan
7 | 2019-02-20 | 2019-02-23 | Salem, Amir |  | 1 | Burullus | Active | Planned | Onshore- Inspection | 3 | Egypt
8 | 2019-02-22 | 2019-03-01 | Carlos Lopez |  | 1 | Vacation | Active | Planned | Offshore | 7 | Egypt
11 | 2019-02-23 | 2019-03-02 | Amir Salem |  | 1 | Petrobel- ZOHR | Active | Planned | Offshore | 7 | Egypt
3 | 2019-02-24 | 2019-03-26 | Wiliam Burnett |  | 1 | DNO | Active | Planned | Onshore | 30 | Kurdistan
2 | 2019-02-28 | 2019-03-10 | Hussein | Shalaby | 2 | Burullus | Vacation | Planned | Offshore | 10 | Egypt, Cairo
10 | 2019-02-28 | 2019-03-14 | Abusaif |  | 1 | Petrobel | Active | Planned | Aburudis | 14 | Egypt
5 | 2019-03-02 | 2019-03-17 | Akram Haroon |  | 1 | Mellitah | Active | Planned | Offshore | 15 | Libya
17 | 2019-03-15 | 2019-03-30 | To be confirmed |  | 1 | OMV | Active | Planned | Inspection | 15 | Tunisia
15 | 2019-03-17 | 2019-03-24 | Akram Haroon |  | 1 | ENI NA | Vacation | Planned | Onshore- Inspection | 7 | Libya
14 | 2019-03-20 | 2019-03-30 | Hussein | Shalaby | 2 | ENI | Active | Planned | Offshore | 10 | Pakistan
9 | 2019-04-01 | 2019-04-13 | AbuSaif |  | 1 | Petrobel | Vacation | Planned | Onshore W563 | 12 | Egypt
4 | 2019-05-01 | 2019-05-06 | AbuSaif |  | 1 | Vacation | Active | Planned | Unsnuffing | 5 | Egypt
12 | 2019-05-01 | 2019-05-11 | Hussein |  | 1 | MOL | Standby | Planned | Stock count | 10 | Pakistan
16 | 2019-07-01 | 2019-07-11 | Hussein |  | 1 | ENI | Active | Planned | Running Assistance | 10 | Tunisia
Formulas:
Finish date = [Expected_date]+6

## Poposed file
Date | Amir | Abusaif | Hussein | Bashar | Carlos Lopez | William Burnett | Shalaby | Akram Haroon
2019-02-17 |  |  | Eni Pakistan | ENI Pakistan | BP |  |  |  | Job | Country | Customer | Job Status | Onshore/ Offshore | String | Expected date | Finish date | duration | # of FSS | FSS1 assigned | FSS2 assigned
2019-02-18 | [8 empty] | 7 | Egypt | BP | Ongoing | Offshore | 9 5/8- 80.8 PPF- C110- TSH Blue Riser | 2019-02-15 | 2019-02-21 | 6 | 1 | Carlos Lopez | N/A
2019-02-19 | [8 empty] | 13 | Pakistan | ENI | Ongoing | Offshore |  | 2019-02-17 | 2019-02-27 | 10 | 2 | Hussein | Bashar
2019-02-20 | Burrullus inspection | [7 empty] | 7 | Egypt | Burullus | Planned | Onshore- Inspection |  | 2019-02-20 | 2019-02-23 | 3 | 1 | Salem, Amir | N/A
2019-02-21 |  |  |  |  | BP |  |  |  | 8 | Egypt | BP | Planned | Offshore |  | 2019-02-21 | 2019-02-28 | 7 | 1 | Carlos Lopez | N/A
2019-02-22 | [8 empty] | 11 | Egypt | Petrobel- ZOHR | Planned | Offshore |  | 2019-02-23 | 2019-03-02 | 7 | 1 | Salem, Amir | N/A
2019-02-23 | Petrobel Zohr | [7 empty] | 3 | Kurdistan | DNO | Planned | Onshore | 16"- 96 PPF- L80- TSH W513 | 2019-02-24 | 2019-03-26 | 30 | 1 | Wiliam Burnett | N/A
2019-02-24 | [5 empty] | DNO |  |  | 2 | Egypt | Burullus | Planned | Offshore | 14- 113 PPF- P110- TSH W623 DPLS in stands | 2019-02-28 | 2019-03-10 | 10 | 2 | Hussein | Shalaby
2019-02-25 | [8 empty] | 10 | Egypt | Petrobel | Planned | Aburudis |  | 2019-02-28 | 2019-03-14 | 14 | 1 | Abusaif | N/A
2019-02-26 | [8 empty] | 5 | Libya | Mellitah | Planned | Offshore | 4 1/2- 11.6 PPF- Sanicro 28- 110 KSI- TSh Blue DPLS | 2019-03-02 | 2019-03-17 | 15 | 1 | Akram Haroon | N/A
2019-02-27 | [8 empty] | 15 | Libya | ENI NA | Planned | Onshore- Inspection |  | 2019-03-17 | 2019-03-24 | 7 | 1 | Akram Haroon | N/A
2019-02-28 |  | Petrobel 3 CR | Burrullus running |  |  |  | Burrullus running |  | 17 | Tunisia | OMV | Planned | Inspection |  | 2019-03-15 | 2019-03-30 | 15 | 1 | To be confirmed | N/A | Fix the visa for shalaby
2019-03-01 | [8 empty] | 14 | Pakistan | ENI | Planned | Offshore |  | 2019-03-20 | 2019-03-30 | 10 | 2 | Hussein | Shalaby | Fix the visa for shalaby
2019-03-02 | [7 empty] | Mellitah | 9 | Egypt | Petrobel | Planned | Onshore W563 |  | 2019-04-01 | 2019-04-13 | 12 | 1 | AbuSaif | N/A
2019-03-03 | [8 empty] | 4 | Egypt | AGIBA | Planned | Unsnuffing | 3 1/2 and 2 7/8 | 2019-05-01 | 2019-05-06 | 5 | 1 | AbuSaif | N/A
2019-03-04 | [8 empty] | 12 | Pakistan | MOL | Planned | Stock count |  | 2019-05-01 | 2019-05-11 | 10 | 1 | Hussein | N/A
2019-03-05 | [8 empty] | 16 | Tunisia | ENI | Planned | Running Assistance |  | 2019-07-01 | 2019-07-11 | 10 | 1 | Hussein | N/A
2019-03-06
2019-03-07
2019-03-08
2019-03-09
2019-03-10
2019-03-11
2019-03-12
2019-03-13
2019-03-14
2019-03-15
2019-03-16
2019-03-17
2019-03-24 |  |  | Eni Pakistan |  |  |  | Eni Pakistan | ENI NA
2019-03-31 |  | Petrobel
2019-04-07
2019-04-14
2019-04-21
2019-04-28 |  | Agiba | MOL
2019-05-05
2019-05-12
2019-05-19
2019-05-26
2019-06-02
2019-06-09
2019-06-16
2019-06-23
2019-06-30 |  |  | ENI Tunisia